## Timeline
Timeline for "Extracting Causal Relations from Electronics & Supply Chain News"
S/N | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | Project Planning | Exploratory Data Analysis | Complete |  | 2023-01-01 | 2023-01-19 | 18 | Meeting on 19 Jan to share current NLP tools performance on data | PHASE 0
2 | Project Planning | Timeline & Plan Setting | Complete |  | 2023-01-19 | 2023-02-02 | 14 | Align across IDS & Panasonic
3 | Causal Extraction | Apply NLP tools on full dataset | Complete |  | 2023-01-30 | 2023-02-13 | 14 | Progress meeting on 10 Feb | PHASE 1
4 | Causal Extraction | Causal relations curation rules | Complete |  | 2023-02-13 | 2023-02-27 | 14 | Progress meeting on 24 Feb
5 | Causal Extraction | Co-reference resolution | Complete |  | 2023-02-27 | 2023-03-13 | 14 | Progress meeting on 09 Mar; Can improve
6 | Causal Extraction | Causal map (store + viz (simple UI)) | Complete |  | 2023-03-13 | 2023-03-27 | 14 | Apart from Cytoscape, how many nodes to show? Do a simple UI on Notebook
7 | Causal Extraction | Evaluation strategy | In Progress |  | 2023-03-27 | 2023-05-15 | 49 | More data needed, deployment needed
8 | Temporal Extraction | Literature Review | Complete |  | 2023-03-20 | 2023-04-10 | 21 |  | PHASE 2
9 | Temporal Extraction | Replicate open-sourced works | In Progress |  | 2023-04-10 | 2023-04-24 | 14
10 | Temporal Extraction | Fine-tuning of codes | Not Started |  | 2023-04-24 | 2023-05-15 | 21
11 | System Building | Combining Causal & Temporal Works + Evaluation | Not Started |  | 2023-05-15 | 2023-06-05 | 21 | Re-run codes, evaluate performance of system at this point
12 | Polarity Extraction | Literature Review | Not Started |  | 2023-06-05 | 2023-06-19 | 14 | Causal polarity: to find if cause and effect args are positive or inversely related | PHASE 3
13 | Polarity Extraction | Replicate open-sourced works | Not Started |  | 2023-06-19 | 2023-07-10 | 21
14 | Polarity Extraction | Fine-tuning of codes | Not Started |  | 2023-07-10 | 2023-07-31 | 21 | Possible issue: Alternative states - "no" & "maybe" claims
15 | System Building | Combining All Works + Evaluation | Not Started |  | 2023-07-31 | 2023-08-14 | 14 | Re-run codes, evaluate performance of system at this point
16 | System Building | Fine-tuning of codes | Not Started |  | 2023-08-14 | 2023-09-25 | 42 | # 16 & 17 done together iteratively | PHASE 4
17 | User Feedback | Gathering Feedback | Not Started |  | 2023-08-21 | 2023-09-25 | 35 | # 16 & 17 done together iteratively
18 | Documentation | Paper Writing - Initial Draft | Not Started |  | 2023-09-18 | 2023-10-16 | 28 |  | PHASE 5
19 | Documentation | Paper Writing - Final Draft | Not Started |  | 2023-10-16 | 2023-11-13 | 28
20 | Documentation | Paper Submission | On Hold |  |  |  | 0 | Conference venues with Jan/Feb 2024 paper deadlines
Formulas:
START DATE = [END DATE, row above]
START DATE = [START DATE, row above]+7
END DATE = [START DATE]+14
END DATE = [START DATE]+14*3